## UIUX problems
Product Name |  | Online Newspaper Site - https://khagracharipratidin.com/ | Test Case Start Date | 2025-06-10 | Test Execution Date | 2025-06-10 | Test Case Summary | Severity (Low / Medium / High)
Module Name |  | UI/UX problems (alignment, design, color, spacing) | Test Case End Date | 2025-11-10 | Test Execution End Date | 2025-06-10 | Pass | High
|  |  | Test Case Developed By | Z | Browser (Tested) |  | Fail | Medium
Developer Name |  | x | Test Case Review By | Supervisor | Performance (Tested) |  | Warning | Low
Test Executed By |  | Farhana Islam |  |  |  |  | Total 68 | Total 68
Bug ID | Bug Title | Steps to Reproduce | Test Data | Expected Result | Actual Result | Severity (Low / Medium / High) | Status (Pass/fail)
UI 001 | Verify that homepage logo alignment is correct | 1. Open homepage 2. Observe logo | N/A | Logo aligned properly | Logo overlaps with menu on small screens | Medium | Fail
UI 002 | Verify that header menu spacing is consistent | 1. Open homepage 2. Inspect menu items | N/A | Menu items evenly spaced | Menu items uneven | Medium | Fail
UI 003 | Verify that font consistency is maintained | 1. Inspect fonts on homepage & articles | N/A | Fonts consistent | Header font differs from article | Low | Fail
UI 004 | Verify that color contrast is sufficient | 1. Compare text & background | N/A | Text readable | Some banner text hard to read | Medium | Fail
UI 005 | Verify that footer alignment is proper | 1. Scroll to footer | N/A | Footer aligned | Footer slightly off-center | Low | Fail
UI 006 | Verify that spacing between sections is consistent | 1. Inspect spacing between blocks | N/A | Sections spaced evenly | Some sections too close | Medium | Fail
UI 007 | Verify that banner image resolution is clear | 1. Inspect homepage banner | N/A | Image clear | Slightly pixelated | Medium | Fail
UI 008 | Verify that button design is consistent | 1. Inspect all buttons | N/A | Buttons uniform | Different colors/fonts | Medium | Fail
UI 009 | Verify that icon alignment is correct | 1. Check social icons | N/A | Icons aligned | Slightly misaligned | Low | Fail
UI 010 | Verify that article title alignment is correct | 1. Open article | N/A | Titles aligned | Titles misaligned with content | Medium | Fail
UI 011 | Verify that hover effects on buttons are working | 1. Hover on buttons | N/A | Buttons animate/change color | Some buttons have no hover | Low | Fail
UI 012 | Verify that navigation bar spacing is consistent | 1. Inspect nav bar | N/A | Links evenly spaced | Links too close | Medium | Fail
UI 013 | Verify that responsive layout on desktop is correct | 1. Open site on desktop | N/A | Layout fits screen | Homepage stretched on large screens | Medium | Fail
UI 014 | Verify that spacing of images in articles is consistent | 1. Open article 2. Inspect images | N/A | Images do not overlap text | Images overlap in some articles | Medium | Fail
UI 015 | Verify that link color is consistent | 1. Inspect links on homepage | N/A | All links same color | Some links differ | Low | Fail
UI 016 | Verify that search bar alignment is correct | 1. Inspect homepage search bar | N/A | Properly aligned | Search bar overlaps menu on small screens | Medium | Fail
UI 017 | Verify that sidebar widget spacing is consistent | 1. Open homepage 2. Inspect sidebar | N/A | Widgets evenly spaced | Widgets too close together | Medium | Fail
UI 018 | Verify that social share button placement is correct | 1. Inspect article page | N/A | Buttons visible and aligned | Misaligned share buttons | Medium | Fail
UI 019 | Verify that padding in article text is consistent | 1. Open article 2. Inspect text blocks | N/A | Consistent padding | Padding inconsistent | Medium | Fail
UI 020 | Verify that newsletter section layout is correct | 1. Scroll to newsletter section | N/A | Proper layout | Section crowded | Medium | Fail
UI 021 | Verify that image captions alignment is correct | 1. Inspect images with captions | N/A | Captions centered | Captions misaligned | Low | Fail
UI 022 | Verify that menu hover design is consistent | 1. Hover menu items | N/A | Hover effect consistent | Some items no effect | Low | Fail
UI 023 | Verify that header spacing on mobile is correct | Open site on mobile | N/A | Proper spacing | Header elements overlap | High | Fail
UI 024 | Verify that article list alignment is correct | 1. Open category page | N/A | Articles aligned | Articles misaligned in grid | Medium | Fail
UI 025 | Verify that banner text spacing is adequate | 1. Inspect banner text | N/A | Adequate spacing | Text too close to edges | Medium | Fail
UI 026 | Verify that sidebar ad alignment is correct | 1. Inspect sidebar ads | N/A | Ads aligned | Ads misaligned | Medium | Fail
UI 027 | Verify that button font size is consistent | 1. Inspect all buttons | N/A | Same font size | Font size varies | Low | Fail
UI 028 | Verify that image gallery spacing is consistent | 1. Open gallery | N/A | Proper spacing between images | Images overlap | Medium | Fail
UI 029 | Verify that sticky header design works correctly | 1. Scroll page | N/A | Header sticky and aligned | Header overlaps content | Medium | Fail
UI 030 | Verify that mobile footer layout is correct | Open site on mobile | N/A | Footer visible and aligned | Footer icons misaligned | Medium | Fail
UI 031 | Verify that image information text is properly align | 1. Click on image news | N/A | Text should be aligned | Header text is left-aligned | Medium | Fail
UI 032 | Verify that broken image or missing thumbnail | 1. Scroll through homepage 2. Check if all article images are visible | N/A | All thumbnails load properly | Some images failed to load | High | Fail
UI 033 | Verify that slider text does not overlap | 1. Open homepage slider 2. Observe text on images 3. Resize window to test responsiveness | N/A | Text should not overlap slider images | Text overlaps images on smaller screens | High | Fail
UI 034 | Verify that footer text is properly aligned | 1. Scroll to footer 2. Check text placement | N/A | Footer text should be aligned left/right consistently | Observed result to be filled after execution | High | Fail
UI 035 | Verify that font sizes are consistent | 1. Navigate to multiple pages 2. Observe headings and body text 3. Compare sizes | N/A | Font sizes should be consistent | Headings and body text sizes vary across pages | Medium | Fail
UI 036 | Verify that the advertisement close (X) button is properly aligned | 1. Open browser | N/A | Advertisement close (X) button is properly aligne | Button is not aigne |  | Fail
UI 037 | Verify that social media links work | 1. Click social media icons 2. Confirm page redirects 3. Check for 404 errors | N/A | Redirect to correct pages | Some icons lead to 404 | High | Fail
UI 038 | Verify that article images are displayed | 1. Open latest news articles 2. Check image loading 3. Compare with article content | N/A | All images should appear | Some images are missing | High | Fail
UI 039 | Verify that article text is error-free | 1. Read any article 2. Check for typos 3. Compare with standard language | N/A | Text should be error-free | Spelling/grammar mistakes present | Medium | Fail
UI 040 | Verify that 'Read More' button works | 1. Click 'Read More' under articles 2. Observe navigation 3. Confirm article opens | N/A | Article should open | Nothing happens | High | Fail
UI 041 | Verify that contact form submits correctly | 1. Fill contact form 2. Submit form 3. Confirm success message | N/A | Form submits successfully | Error appears, not submitted | High | Fail
UI 042 | Verify that comment section loads | 1. Open article comments 2. Check loading 3. Confirm comments appear | N/A | Comments load correctly | Comments section fails to load | High | Fail
UI 043 | Verify that video playback works | 1. Click embedded videos 2. Observe playback 3. Confirm video plays | N/A | Videos play normally | Video does not play | High | Fail
UI 044 | Verify that newsletter signup works | 1. Submit email for newsletter 2. Observe confirmation 3. Confirm signup success | N/A | Signup success message | Error displayed, no signup | Medium | Fail
UI 045 | Verify that layout adjusts on mobile | 1. Open site on mobile 2. Observe content 3. Confirm proper alignment | N/A | Content fits screen | Content overflows, misaligned | High | Fail
UI 046 | Verify that mobile navigation works | 1. Click hamburger menu 2. Observe menu opening 3. Confirm navigation links accessible | N/A | Menu opens | Menu does not open | High | Fail
UI 047 | Verify that images scale on mobile | 1. View gallery on mobile 2. Observe images 3. Confirm images fit screen | N/A | Images fit screen | Images cut off | Medium | Fail
UI 048 | Verify that text does not overlap buttons on mobile | 1. Open homepage on phone 2. Observe button areas 3. Confirm text placement | N/A | Text and buttons separated | Text overlaps buttons | High | Fail
UI 049 | Verify that dropdown menu works on mobile | 1. Click dropdown menu 2. Observe expansion 3. Confirm all items accessible | N/A | Menu expands | Menu does not expand | High | Fail
UI 050 | Verify that homepage loads quickly | 1. Open homepage 2. Measure load time 3. Confirm load under 3 seconds | N/A | Load within 3 seconds | Takes over 10 seconds | High | Fail
UI 051 | Verify that console has no errors | 1. Open homepage 2. Open browser console 3. Observe errors | N/A | No errors | Multiple JS errors | Medium | Fail
UI 052 | Verify that image-heavy pages load quickly | 1. Open image gallery 2. Observe loading 3. Confirm page loads under 5s | N/A | Load in under 5s | Page takes 12s | Medium | Fail
UI 053 | Verify that lazy loading works | 1. Scroll down homepage 2. Observe image loading 3. Confirm progressive loading | N/A | Images load progressively | Images fail to load until refresh | Medium | Fail
UI 054 | Verify that caching does not display old content | 1. Reload pages 2. Observe content 3. Confirm current content displayed | N/A | Pages load instantly | Old content shown due to caching | Low | Fail
UI 055 | Verify that carousel navigation buttons appear | 1. Go to homepage slider 2. Observe navigation arrows 3. Confirm arrows visible | N/A | Navigation arrows visible | Arrows missing | Medium | Fail
UI 056 | Verify that card layouts are consistent | 1. Open news section 2. Observe card alignment 3. Confirm uniform layout | N/A | Cards align uniformly | Cards misaligned | Medium | Fail
UI 057 | Verify that popups do not cover content | 1. Trigger newsletter popup 2. Observe popup position 3. Confirm content visible | N/A | Popup should not cover important content | Popup hides article title | High | Fail
UI 058 | Verify that breadcrumb navigation is aligned | 1. Open article page 2. Observe breadcrumbs 3. Confirm proper alignment | N/A | Breadcrumb aligns properly | Breadcrumb shifted left | Low | Fail
UI 059 | Verify that sidebar icon sizes are consistent | 1. View sidebar icons 2. Observe icon size 3. Compare sizes | N/A | Icons have same size | Icons differ in size | Low | Fail
UI 060 | Verify that PDF download links work | 1. Click PDF links 2. Observe download 3. Confirm file downloaded | N/A | PDF downloads | Link leads to 404 | High | Fail
UI 061 | Verify that external references are correct | 1. Click references 2. Observe redirection 3. Confirm correct page | N/A | Redirect to correct sites | Some links incorrect | Medium | Fail
UI 062 | Verify that text is fully visible in portrait mode | 1. Rotate device portrait 2. Observe text display 3. Confirm no truncation | N/A | Text fully visible | Text truncated | Medium | Fail
UI 063 | Verify that sticky header does not overlap content | 1. Scroll on mobile 2. Observe header 3. Confirm content visible | N/A | Header adjusts | Header overlaps first section | Medium | Fail
UI 064 | Verify that homepage memory usage is normal | 1. Open homepage 2. Observe memory usage 3. Confirm normal levels | N/A | Normal memory usage | Browser consumes excessive memory | Medium | Fail
UI 065 | Verify that images load quickly | 1. Open gallery 2. Observe image loading 3. Confirm quick load | N/A | Images load quickly | Images take too long to appear | Medium | Fail
UI 066 | Verify that animations run smoothly | 1. Scroll homepage 2. Observe animations 3. Confirm smooth playback | N/A | Smooth animations | Animations choppy | Low | Fail
UI 067 | Verify that video autoplay is smooth | 1. Open video 2. Observe playback 3. Confirm smooth autoplay | N/A | Video plays smoothly | Video stutters | Medium | Fail
UI 068 | Verify that form validation works | 1. Submit contact form with empty fields 2. Observe validation messages 3. Confirm form does not submit | N/A | Validation messages appear | Form submits anyway | High | Fail

## Broken links, missing images, o
Product Name |  | Online Newspaper Site - https://khagracharipratidin.com/ | Test Case Start Date | 2025-06-10 | Test Execution Date | 2025-06-10 | Test Case Summary
Module Name |  | Broken links, missing images, or text errors | Test Case End Date | 2025-11-10 | Test Execution End Date | 2025-06-10 | Pass
|  |  | Test Case Developed By | Z | Browser (Tested) |  | Fail
Developer Name |  | x | Test Case Review By | Supervisor | Performance (Tested) |  | Warning
Test Executed By |  | Farhana Islam |  |  |  |  | Total
Bug ID | Bug Title | Steps to Reproduce | Test Data | Expected Result | Actual Result | Severity (Low / Medium / High) | Status(Pass/Fail)
BL001 | Verify that all main menu links navigate correctly | 1. Click each main menu link | N/A | Pages open correctly | Some links return 404 | High | Fail
BL002 | Verify that all footer links navigate correctly | 1. Click each footer link | N/A | Correct pages open | Some links dead | Medium | Fail
BL003 | Verify that sidebar links work properly | 1. Click sidebar category links | N/A | Category loads correctly | Some categories missing | Medium | Fail
BL004 | Verify that homepage article links open | 1. Click article thumbnails/titles | N/A | Articles load properly | Some articles 404 | High | Fail
BL005 | Verify that image thumbnails load correctly | 1. Open homepage | N/A | Images visible | Broken thumbnails | High | Fail
BL006 | Verify that banner ads load without errors | 1. Open homepage | N/A | Banner images display | Missing banners | Medium | Fail
BL007 | Verify that author images load on article pages | 1. Open article pages | N/A | Author image loads | Broken image icon | Low | Fail
BL008 | Verify that logo displays properly | 1. Open homepage | N/A | Logo visible | Logo not loading | High | Fail
BL009 | Verify that social media icons load correctly | 1. Scroll to footer > check icons | N/A | Icons display | Some missing icons | Medium | Fail
BL010 | Verify that contact page map image loads | 1. Open contact page | N/A | Map visible | Map not loading | Medium | Fail
BL011 | Verify that article body text has no spelling errors | 1. Open articles > scan text | N/A | No spelling errors | Multiple spelling issues | Medium | Fail
BL012 | Verify that article titles have no spelling errors | 1. Check article headlines | N/A | No spelling mistakes | Errors in headlines | High | Fail
BL013 | Verify that the About Us page text is grammatically correct | 1. Open About Us | N/A | Correct grammar | Errors found | Low | Fail
BL014 | Verify that meta descriptions are correct | 1. Inspect page meta tags | N/A | Meta text is correct | Spelling/typos in meta | Low | Fail
BL015 | Verify that category pages show correct names | 1. Navigate category pages | N/A | Correct category names | Misspelled names | Medium | Fail
BL016 | Verify that images in category pages load | 1. Open each category page | N/A | Images visible | Broken images | Medium | Fail
BL017 | Verify that pagination links work properly | 1. Navigate to next/previous pages | N/A | Pagination works | Links broken | High | Fail
BL018 | Verify that RSS feed link works | 1. Click RSS feed link | N/A | RSS feed loads | Link broken | Low | Fail
BL019 | Verify that publication date displays correctly | 1. Open article pages | N/A | Correct date displayed | Dates missing/incorrect | Medium | Fail
BL020 | Verify that author names are displayed correctly | 1. Open article pages | N/A | Correct author names | Missing/wrong names | Medium | Fail

## Functional errors or non-workin
Product Name |  | Online Newspaper Site - https://khagracharipratidin.com/ | Test Case Start Date | 2025-06-10 | Test Execution Date | 2025-06-10 | Test Case Summary
Module Name |  | Functional errors or non-working buttons | Test Case End Date | 2025-11-10 | Test Execution End Date | 2025-06-10 | Pass 0
|  |  | Test Case Developed By | Z | Browser (Tested) |  | Fail 20
Developer Name |  | x | Test Case Review By | Supervisor | Performance (Tested) |  | Warning 0
Test Executed By |  | Farhana Islam |  |  |  |  | Total 20
Bug ID | Bug Title | Steps to Reproduce | Test Data | Expected Result | Actual Result | Severity (Low / Medium / High) | Status
FN001 | Verify that the search button functions correctly | 1. Enter query 2. Click search | news | Relevant results displayed | No response | High | Fail
FN002 | Verify that the login button works with valid credentials | 1. Enter valid username/password 2. Click login | Valid credentials | User logged in successfully | Login fails | High | Fail
FN003 | Verify that the login button rejects invalid credentials | 1. Enter invalid username/password 2. Click login | Invalid credentials | Error message shown | No validation | High | Fail
FN004 | Verify that the signup button redirects to registration page | 1. Click signup button | N/A | Registration page opens | No response | Medium | Fail
FN005 | Verify that the subscribe button for newsletter works | 1. Enter email 2. Click subscribe | Valid email | Confirmation shown | No confirmation | Medium | Fail
FN006 | Verify that the contact form submit button works | 1. Fill contact form 2. Click submit | Sample data | Form submitted | No response | High | Fail
FN007 | Verify that the comment post button works | 1. Enter comment 2. Click post | Sample comment | Comment posted | Button unresponsive | Medium | Fail
FN008 | Verify that social media share buttons work | 1. Click Facebook/Twitter share button | N/A | Redirects to share page | Nothing happens | Low | Fail
FN009 | Verify that navigation bar links function | 1. Click navigation links | N/A | Correct page loads | No action | High | Fail
FN010 | Verify that the 'Read More' button works on articles | 1. Click 'Read More' | N/A | Full article opens | No redirection | Medium | Fail
FN011 | Verify that the search input accepts text | 1. Type text in search field | sample | Text accepted | Field unresponsive | Low | Fail
FN012 | Verify that video play button functions | 1. Open article with video 2. Click play | N/A | Video plays | No playback | High | Fail
FN013 | Verify that audio play button functions | 1. Open audio post 2. Click play | N/A | Audio plays | No playback | Medium | Fail
FN014 | Verify that the back-to-top button works | 1. Scroll down page 2. Click back-to-top | N/A | Page scrolls to top | No action | Low | Fail
FN015 | Verify that language switch button works | 1. Click language switch button | N/A | Language changes | No response | Medium | Fail
FN016 | Verify that dropdown menus expand/collapse | 1. Hover/click menu item | N/A | Submenu displays | Menu stuck | Medium | Fail
FN017 | Verify that image gallery next/prev buttons work | 1. Open gallery 2. Click next/prev | N/A | Images change | No response | Low | Fail
FN018 | Verify that the print button works | 1. Open article 2. Click print button | N/A | Print dialog opens | Nothing happens | Low | Fail
FN019 | Verify that the download button works | 1. Open resource 2. Click download | PDF/Doc file | File downloads | No action | Medium | Fail
FN020 | Verify that live chat button opens chat window | 1. Click chat button | N/A | Chat window opens | No response | High | Fail

## Mobile responsiveness issues
Product Name |  | Online Newspaper Site - https://khagracharipratidin.com/ | Test Case Start Date | 2025-06-10 | Test Execution Date | 2025-06-10 | Test Case Summary
Module Name |  | Mobile responsiveness issues | Test Case End Date | 2025-11-10 | Test Execution End Date | 2025-06-10 | Pass
|  |  | Test Case Developed By | Z | Browser (Tested) |  | Fail
Developer Name |  | x | Test Case Review By | Supervisor | Performance (Tested) |  | Warning
Test Executed By |  | Farhana Islam |  |  |  |  | Total 20
Bug ID | Bug Title | Steps to Reproduce | Test Data | Expected Result | Actual Result | Severity (Low / Medium / High) | Status(pass/Fail)
MR 001 | Verify that homepage layout adjusts on mobile screens | 1. Open homepage on mobile | N/A | Layout adapts properly | Layout overlaps | High | Fail
MR 002 | Verify that navigation menu collapses into hamburger menu | 1. Open site on mobile | N/A | Hamburger menu visible | Menu items overflow | High | Fail
MR 003 | Verify that hamburger menu expands when clicked | 1. Click hamburger icon | N/A | Menu expands fully | Menu not expanding | High | Fail
MR 004 | Verify that logo scales correctly on mobile | 1. Open homepage on mobile | N/A | Logo resizes proportionally | Logo too large | Medium | Fail
MR 005 | Verify that article text is readable without zooming | 1. Open articles on mobile | N/A | Text readable | Text too small | High | Fail
MR 006 | Verify that images resize correctly | 1. Open homepage and articles on mobile | N/A | Images resize without distortion | Images overflow container | Medium | Fail
MR 007 | Verify that banners adjust proportionally | 1. Open homepage on mobile | N/A | Banners scale | Banner cuts off | Medium | Fail
MR 008 | Verify that footer sections align properly on mobile | 1. Scroll to footer on mobile | N/A | Footer items stack neatly | Items overlap | Medium | Fail
MR 009 | Verify that sidebars reposition or hide on mobile | 1. Open homepage on mobile | N/A | Sidebars hidden/repositioned | Sidebar overlaps content | High | Fail
MR 010 | Verify that article thumbnails resize properly | 1. Open homepage on mobile | N/A | Thumbnails resize correctly | Thumbnails cropped | Medium | Fail
MR 011 | Verify that article titles wrap properly on small screens | 1. Open homepage on mobile | N/A | Titles wrap to new line | Titles cut off | Medium | Fail
MR 012 | Verify that spacing between sections is consistent on mobile | 1. Scroll homepage on mobile | N/A | Sections evenly spaced | Inconsistent spacing | Low | Fail
MR 013 | Verify that ads resize correctly on mobile | 1. Open site with ads | N/A | Ads scale properly | Ads overlap content | Medium | Fail
MR 014 | Verify that comment form fits on mobile screen | 1. Open article > scroll to comment form | N/A | Form fields visible | Fields overflow | Medium | Fail
MR 015 | Verify that buttons are clickable on mobile | 1. Open site on mobile > tap buttons | N/A | Buttons respond to tap | Some too small to tap | High | Fail
MR 016 | Verify that dropdown menus open correctly on mobile | 1. Tap dropdown menus | N/A | Dropdowns open | Not opening | High | Fail
MR 017 | Verify that pagination works correctly on mobile | 1. Scroll homepage > tap next/prev | N/A | Pages load correctly | Links overlap | Medium | Fail
MR 018 | Verify that the search bar displays properly | 1. Open homepage on mobile | N/A | Search bar visible | Search bar cut off | Medium | Fail
MR 019 | Verify that video embeds resize on mobile | 1. Open article with video | N/A | Videos responsive | Video extends off-screen | High | Fail
MR 020 | Verify that scrolling works smoothly on mobile | 1. Scroll page on mobile | N/A | Smooth scrolling | Jerky scrolling | Low | Fail

## Performance problems
Product Name |  | Online Newspaper Site - https://khagracharipratidin.com/ | Test Case Start Date | 2025-06-10 | Test Execution Date | 2025-06-10 | Test Case Summary
Module Name |  | Performance problems | Test Case End Date | 2025-11-10 | Test Execution End Date | 2025-06-10 | Pass
|  |  | Test Case Developed By | Z | Browser (Tested) |  | Fail
Developer Name |  | x | Test Case Review By | Supervisor | Performance (Tested) |  | Warning
Test Executed By |  | Farhana Islam |  |  |  |  | Total
Bug ID | Bug Title | Steps to Reproduce | Test Data | Expected Result | Actual Result | Severity (Low / Medium / High) | Status (Pass/Fail)
PP001 | Verify that homepage loads within 3 seconds | 1. Open homepage | N/A | Page loads in ≤3s | Loads in 6s | High | Fail
PP002 | Verify that article pages load within 3 seconds | 1. Open article page | N/A | Page loads in ≤3s | Loads in 5s | High | Fail
PP003 | Verify that navigation between pages is smooth | 1. Navigate through menu | N/A | Pages load instantly | Delay observed | Medium | Fail
PP004 | Verify that console logs show no errors | 1. Open dev tools 2. Load site | N/A | No errors in console | Multiple JS errors | High | Fail
PP005 | Verify that CSS files load without delay | 1. Inspect network requests | N/A | CSS loads <1s | CSS loads slowly | Medium | Fail
PP006 | Verify that JS files load efficiently | 1. Inspect network requests | N/A | JS loads <1s | Large JS delay | High | Fail
PP007 | Verify that images are optimized | 1. Open homepage 2. Inspect network | N/A | Optimized images | Large image sizes | High | Fail
PP008 | Verify that lazy loading is enabled for images | 1. Scroll homepage | N/A | Images load on scroll | All load upfront | Medium | Fail
PP009 | Verify that caching is enabled | 1. Reload site | N/A | Page reloads faster | Reloads slowly | High | Fail
PP010 | Verify that CDN is used for static resources | 1. Inspect resource URLs | N/A | CDN used | No CDN in use | Medium | Fail
PP011 | Verify that database response time is optimal | 1. Open article list | N/A | Query returns fast | Slow DB fetch | High | Fail
PP012 | Verify that no unused CSS is loaded | 1. Audit with DevTools | N/A | No unused CSS | Large unused CSS | Medium | Fail
PP013 | Verify that no unused JS is loaded | 1. Audit with DevTools | N/A | No unused JS | Many unused scripts | Medium | Fail
PP014 | Verify that Google PageSpeed score > 80 | 1. Test with PageSpeed | N/A | Score ≥80 | Score 45 | High | Fail
PP015 | Verify that First Contentful Paint < 2s | 1. Test with Lighthouse | N/A | FCP <2s | 4s | High | Fail
PP016 | Verify that Largest Contentful Paint < 3s | 1. Test with Lighthouse | N/A | LCP <3s | 6s | High | Fail
PP017 | Verify that Time to Interactive < 5s | 1. Test with Lighthouse | N/A | TTI <5s | 8s | High | Fail
PP018 | Verify that Cumulative Layout Shift < 0.1 | 1. Scroll homepage | N/A | CLS <0.1 | CLS 0.3 | Medium | Fail
PP019 | Verify that mobile performance is optimal | 1. Test site on mobile | N/A | Mobile loads fast | Slow load | High | Fail
PP020 | Verify that server response time < 200ms | 1. Ping server | N/A | <200ms | 500ms | High | Fail
PP021 | Verify that GZIP compression is enabled | 1. Inspect headers | N/A | GZIP active | Not enabled | Medium | Fail
PP022 | Verify that duplicate network requests are avoided | 1. Inspect network | N/A | No duplicates | Duplicate CSS calls | Medium | Fail
PP023 | Verify that homepage scroll is smooth | 1. Scroll homepage | N/A | Smooth scroll | Choppy scroll | Low | Fail
PP024 | Verify that fonts load efficiently | 1. Inspect font requests | N/A | Fonts load <1s | Delay in font load | Medium | Fail
PP025 | Verify that favicon loads correctly | 1. Open site 2. Check tab icon | N/A | Favicon loads | Favicon missing | Low | Fail
PP026 | Verify that redirections are minimized | 1. Inspect network | N/A | Few/no redirects | Multiple redirects | Medium | Fail
PP027 | Verify that async/defer is used for JS | 1. Inspect script tags | N/A | Scripts async/defer | No async usage | Medium | Fail
PP028 | Verify that request count is under 100 | 1. Audit with DevTools | N/A | <100 requests | 180 requests | Medium | Fail
PP029 | Verify that homepage weight is <1.5MB | 1. Audit network | N/A | Page <1.5MB | 3.2MB | High | Fail
PP030 | Verify that no memory leaks occur in console | 1. Monitor memory in DevTools | N/A | No leaks | Memory leaks found | High | Fail
PP031 | verify that image and news update | 1. Open any image with news | N/A | Images load successfully | Not loded successfully | High | Fail